## project
Project Planner
[7 empty] | Period Highlight: |  |  |  |  | 31 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PERSON | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | RESPONSIBLE | START | DURATION | START | DURATION | COMPLETE | PERIODS
[7 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
[7 empty] | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
WINTER BREAK
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Project Plan | Sarfaraz | 1 | 1 | 1 | 2 | 100%
Request for Product | Sumeet | 2 | 1 | 2 | 1 | 100%
Feature Description | Dalip | 2 | 1 | 2 | 1 | 100%
Resource List | Sarfaraz | 2 | 1 | 3 | 1 | 100%
UML Diagram Maker | Dalp | 3 | 2 | 3 | 1 | 100%
Planning Milestone
Improve Bank Programs | Dalip & Sumeet | 4 | 2 | 9 | 2 | 100%
Chips Class | Sarfaraz | 4 | 2 | 10 | 1 | 100%
Deck Class | Sarfaraz | 22 | 2 | 10 | 1 | 100%
BJackPlayer Class | Dalip | 22 | 2 | 17 | 1 | 100%
PokerPlayer Class | Sumeet | 22 | 2 | 22 | 3 | 100%
Player Milestone
BJackUI | Dalip | 24 | 8 | 22 | 9 | 90%
PokerUI | Sumeet | 24 | 8 | 22 | 9 | 60%
MenuUI | Sarfaraz | 24 | 8 | 26 | 5 | 20%
Customer Meeting #1 | Team | 28 | 1 | 28 | 1 | 100%
UI Milestone
Integrated Testing | Sumeet | 31 | 3 |  |  | 0%
Integrated Testing | Sarfaraz | 31 | 3 |  |  | 0%
Integrated Testing | Dalip | 31 | 3 |  |  | 0%
Poker Documentation | Sumeet | 33 | 4 |  |  | 0%
Menu Documentation | Sarfaraz | 33 | 4 |  |  | 0%
Black Jack Documentation | Dalip | 33 | 4 |  |  | 0%
Customer Meeting #2 | Team | 35 | 1 |  |  | 0%
Final Product | Team | 36 | 1